## Instructions
BuildersCalc.Pro - Construction Gantt Chart Templates
How to use these templates:
1. Choose the sheet that matches your project type.
2. Adjust Start Week (col D) and Duration (col E) for each task.
3. Blue bars show task duration. Orange cells mark milestones.
4. Add or delete rows as needed for your project.
Columns: A=Ref B=Task Name C=Trade D=Start Week E=Duration (weeks) F=Notes
Download more free construction templates at BuildersCalc.Pro

## House Extension
House Extension - Construction Programme
Ref | Task Name | Trade / Responsible | Start Wk | Duration (wks) | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
PRE-CONSTRUCTION
1 | Building Control Application | Client / Builder | 1 | 2 | Submit before site start
2 | Contractor Tender & Selection | Client | 1 | 3 | Get min. 3 quotes
3 | Pre-Start Meeting | Client / Builder | 3 | 1 | Agree programme & site rules
GROUNDWORKS & STRUCTURE
4 | Site Set-Up, Hoardings & Skip | Builder | 4 | 1
5 | Strip Out (if applicable) | Builder | 4 | 1
6 | Excavate Foundations | Groundworker | 5 | 2
7 | Drainage - New Runs | Groundworker | 5 | 2
8 | BC Inspection - Foundations | Building Control | 7 | 1 | Cannot backfill until inspected
9 | Blockwork to DPC | Bricklayer | 7 | 1
10 | BC Inspection - DPC Level | Building Control | 8 | 1
11 | Oversite Preparation & Slab | Groundworker | 8 | 1
SUPERSTRUCTURE
12 | External Walls to Wall Plate | Bricklayer | 9 | 4
13 | Structural Steel & Lintels | Structural Steel | 9 | 2 | Allow 4-6 wk lead time
14 | Roof Carpentry | Carpenter | 13 | 2
15 | Roof Covering | Roofer | 15 | 1
16 | ** WEATHERTIGHT ** |  | 16 | 0
FIRST FIX
17 | Windows & External Doors | Window Co. | 16 | 1
18 | First Fix Electrics | Electrician | 17 | 1
19 | First Fix Plumbing | Plumber | 17 | 1
20 | First Fix Carpentry | Carpenter | 17 | 1
21 | BC Inspection - First Fix | Building Control | 18 | 1
22 | Insulation | Insulation Co. | 18 | 1
23 | Drylining / Boarding | Dryliner | 19 | 1
SECOND FIX & FINISHING
24 | Plastering | Plasterer | 20 | 2
25 | Drying-Out Period |  | 22 | 2 | Do not start 2nd fix early
26 | Second Fix Electrics | Electrician | 24 | 1
27 | Second Fix Plumbing | Plumber | 24 | 1
28 | Internal Joinery | Carpenter | 24 | 1
29 | Decoration | Decorator | 25 | 1
30 | Flooring | Flooring Co. | 26 | 1
31 | Kitchen / Bathroom Fit-Out | Specialist | 26 | 1
32 | External Works & Landscaping | Builder | 26 | 2
33 | BC Final Inspection | Building Control | 27 | 1
34 | Snagging | Builder | 28 | 1
35 | ** PRACTICAL COMPLETION ** |  | 28 | 0

## Loft Conversion
Loft Conversion - Construction Programme
Ref | Task Name | Trade / Responsible | Start Wk | Duration (wks) | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
PRE-CONSTRUCTION
1 | Building Regs Application | Client / Builder | 1 | 1
2 | Party Wall Agreement (if req'd) | Client / Surveyor | 1 | 4 | Allow 2 months min.
3 | Contractor Appointment | Client | 1 | 2
4 | Pre-Start Meeting | Client / Builder | 2 | 1
STRUCTURE
5 | Scaffold Erect | Scaffolder | 3 | 1
6 | Roof Open Up & Dormer Frame | Carpenter | 4 | 2
7 | Structural Steel (if req'd) | Steel Erector | 4 | 1
8 | Roofing - Covering & Dormers | Roofer | 6 | 1
9 | Dormer Cheeks & Framing | Carpenter | 6 | 2
10 | Velux / Rooflights | Roofer / Carpenter | 6 | 1
11 | ** WEATHERTIGHT ** |  | 8 | 0
FIRST FIX
12 | Staircase Carcase | Carpenter | 8 | 1
13 | First Fix Electrics | Electrician | 9 | 1
14 | First Fix Plumbing | Plumber | 9 | 1
15 | Insulation (roof & floor) | Insulation Co. | 9 | 1
16 | BC Inspection - First Fix | Building Control | 10 | 1
17 | Boarding | Dryliner | 10 | 1
FINISHING
18 | Plastering | Plasterer | 11 | 2
19 | Drying Out |  | 13 | 1
20 | Second Fix Electrics | Electrician | 14 | 1
21 | Second Fix Plumbing | Plumber | 14 | 1
22 | Staircase Finish | Carpenter | 14 | 1
23 | Decoration | Decorator | 15 | 1
24 | Flooring | Flooring Co. | 16 | 1
25 | Scaffold Strike | Scaffolder | 16 | 1
26 | BC Final Inspection | Building Control | 17 | 1
27 | Snagging | Builder | 18 | 1
28 | ** PRACTICAL COMPLETION ** |  | 18 | 0

## Groundworks - New Build
Groundworks - New Build - Construction Programme
Ref | Task Name | Trade / Responsible | Start Wk | Duration (wks) | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
SETTING OUT & PREPARATION
1 | Setting Out | Builder / Engineer | 1 | 1 | From engineer's drawings
2 | Topsoil Strip & Stockpile | Groundworker | 1 | 1
3 | Bulk Excavation | Groundworker | 2 | 2
DRAINAGE
4 | Foul Drainage Runs | Groundworker | 2 | 3
5 | Surface Water Drainage | Groundworker | 3 | 3
6 | Connection to Sewer (if req'd) | Groundworker / Water Co. | 3 | 2 | Requires utility notification
7 | Drainage Inspection (CCTV) | Building Control | 5 | 1
FOUNDATIONS
8 | Trench Excavation | Groundworker | 4 | 2
9 | BC Inspection - Trench | Building Control | 6 | 1 | Do not pour until inspected
10 | Foundation Concrete Pour | Groundworker | 6 | 1
11 | Blockwork to DPC | Bricklayer | 7 | 2
12 | BC Inspection - DPC | Building Control | 9 | 1
13 | Hardcore Fill & Compaction | Groundworker | 9 | 1
14 | DPM & Insulation | Groundworker | 10 | 1
SLAB & SERVICES
15 | Gas / Electric / Water Ducting | Service contractor | 9 | 2
16 | Underfloor Heating (if req'd) | UFH Contractor | 11 | 1
17 | Ground Floor Slab Pour | Groundworker | 12 | 1
18 | Curing & Protection |  | 13 | 1 | Min. 7 days before loading
19 | Backfill External Walls | Groundworker | 13 | 1
20 | Temporary Works Strike | Builder | 14 | 1
21 | ** READY FOR SUPERSTRUCTURE ** |  | 14 | 0